## Instructions
Introduction
In order to assure that the 111 Provider can roll-out GP Connect it is advisable that they complete a single test to each of the different GP IT systems. This will provide the DUEC (Digital Urgent and Emergency Care) and CCG teams assurance that the tecnology works as expected. This is not just the booking standards but the whole end to end process.
Pre-Requisites for Testing | Owner | Complete
Identify the test surgery to be used | NHSD - IBC
Necessary configuration on the surgery system has been completed | NHSD - IBC
Ensure that the test patient has been set-up correctly. See https://pcse.england.nhs.uk/services/registrations for additional guidance | NHSD - IBC
Necessary configuration on the 111 IT system has been completed | NHSD - UEC
111 Provider understands the necessary steps to get to the booking button / screens (i.e. NHS Pathways / DOS screens) | 111 Provider
The Surgery is profiled correctly on the Directory of Services | DOS Lead
The Surgery has updated instructions | DOS Lead
The Sugery has the correct referral role | DOS Lead
The Surgery has a primary end point (for ITK / Email referrals) | DOS Lead
Update test plan for all dispositons codes that will support appointment booking | NHSD - UEC
Update the test plan with the surgery IT System that will be tested | NHSD - IBC
Update the test plan (add data to the highlighted fields) | NHSD - IBC
Update the test plan appointment slot data (so that the 111 Provider understands what informaiton they will receive) | NHSD - IBC
Organise a testing call using (screen sharing) call between all stakeholders. This should be tested before any calls are scheduled. | NHSD - IBC
Testing Process
The 111 Provider will run though the end to end process to book an appointment for each relevent disposition code. Any issues wil be owned by NHSD to resolve with the appropriate 3rd parties.

## 111 to GP Test Plan
111 to GP (GP Connect) Operational Test Plan
Surgery IT System
GP IT System |  | Book into EMIS
Testing Date & Time
Go-live Date & Time
Surgery Details (Main)
Surgery Name:
Surgery DoS name:
Surgery DoS ID:
Surgery Lead:
Surgery Address:
Surgery Postcode:
Surgery Tel:
Surgery Details (Branch - if applicable)
Surgery Name:
Surgery DoS name:
Surgery DoS ID:
Surgery Lead:
Surgery Address:
Surgery Postcode:
Surgery Tel:
Stakeholders |  | Name | Email | Phone | Test Team
CCG Lead: |  |  |  |  | Yes / No
STP Lead: |  |  |  |  | Yes / No
NHS England Lead: |  |  |  |  | Yes / No
DOS Lead: |  |  |  |  | Yes
Surgery Lead: |  |  |  |  | Yes
Surgery IT Supplier Lead: |  |  |  |  | Yes
NHS Digital Lead (GP Connect): |  |  |  |  | Yes
NHS Digital Lead (UEC): |  |  |  |  | Yes
111 IT Supplier Lead: |  |  |  |  | Yes
111 Provider Lead |  |  |  |  | Yes
Appointment Booking
Length of appointments |  | 10 mins
Day |  | Opening hours | Appointment booking slots |  | Appointments per day
B/H |  | Closed
Monday |  | 09:00 to 17:00 | 09:30,10:30, 11:30, 12:30, 13:30, 14:30 |  | 6
Tuesday |  | 09:00 to 17:00 | 09:30,10:30, 11:30, 12:30, 13:30, 14:30 |  | 6
Wednesday |  | 09:00 to 17:00 | 09:30,10:30, 11:30, 12:30, 13:30, 14:30 |  | 6
Thursday |  | 09:00 to 17:00 | 09:30,10:30, 11:30, 12:30, 13:30, 14:30 |  | 6
Friday |  | 09:00 to 17:00 | 09:30,10:30, 11:30, 12:30, 13:30, 14:30 |  | 6
Saturday |  | 09:00 to 13:00 | 09:30,10:30, 11:30, 12:30, 13:30, 14:30 |  | 6
Sunday |  | Closed
Test Patient Name
Patient's Name
Patient's NHS Number
Patient's DOB
Patient's Current Address |  | 0
Patient's Curent Postcode |  | 0
Patient's Surgery |  | 0
Test Plan
Disposition Code | Test ID | Assurance Criteria | Expected Result | Pass / Fail | Comments
Dx05 | 1 | Is the user able to select the appointment botton for this DX code? | The user can select the button and no errors are presented
| 2 | Is the user presented with a list of appointment slots to book into when pressing the appointment button? | The user should see all the appointments available above (apart from those already booked or taken)
| 3 | Is the user presented with all clinics that have been made available to the 111 service? | The user should be presented with a list of appropriate clinics/appointment types |  | Including Branch surgery locations
| 4 | Is the user able to book an appointment? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 5 | Is the user able to book an appointment at a branch/different location? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 6 | Is the user able to change/re-book the appointment whilst in the same consultation? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 7 | Is a SMS sent to the patient (if configured)? | The patient receives a SMS and it contains the correct appointment and location details
| 8 | Is the user able to change/re-book the appointment after the consultation is complete (the patient calls back in 2 hours)? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 9 | Is the user able to cancel the appointment after the consultation is complete (the patient calls back in 2 hours)? | The user is presented with a confirmation that the booking has been succesful The appointment at the surgery is cancelled within their IT system
| 10 | Is a referral message sent successfully? | The 111 provider gets confirmation tat the referral was sent
| 11 | Is a referral message received successfully? | The surgery will be able to view the referral information in their surgery system
| 12 | Is the user presented with no appointments when no appointments are available? | The user should see no appointments are being displayed and appropriate message is displayed
| 13 | Is the user able to run the standard GP Connect reports? | User can locate the reports and successfully run them
Dx06 | 14 | Is the user able to select the appointment botton for this DX code? | The user can select the button and no errors are presented
| 15 | Is the user presented with a list of appointment slots to book into when pressing the appointment button? | The user should see all the appointments available above (apart from those already booked or taken)
| 16 | Is the user presented with all clinics that have been made available to the 111 service? | The user should be presented with a list of appropriate clinics/appointment types |  | Including Branch surgery locations
| 17 | Is the user able to book an appointment? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 18 | Is the user able to book an appointment at a branch/different location? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 19 | Is the user able to change/re-book the appointment whilst in the same consultation? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 20 | Is a SMS sent to the patient (if configured)? | The patient receives a SMS and it contains the correct appointment and location details
| 21 | Is the user able to change/re-book the appointment after the consultation is complete (the patient calls back in 2 hours)? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 22 | Is the user able to cancel the appointment after the consultation is complete (the patient calls back in 2 hours)? | The user is presented with a confirmation that the booking has been succesful The appointment at the surgery is cancelled within their IT system
| 23 | Is a referral message sent successfully? | The 111 provider gets confirmation tat the referral was sent
| 24 | Is a referral message received successfully? | The surgery will be able to view the referral information in their surgery system
| 25 | Is the user presented with no appointments when no appointments are available? | The user should see no appointments are being displayed and appropriate message is displayed
| 26 | Is the user able to run the standard GP Connect reports? | User can locate the reports and successfully run them
Dx07 | 27 | Is the user able to select the appointment botton for this DX code? | The user can select the button and no errors are presented
| 28 | Is the user presented with a list of appointment slots to book into when pressing the appointment button? | The user should see all the appointments available above (apart from those already booked or taken)
| 29 | Is the user presented with all clinics that have been made available to the 111 service? | The user should be presented with a list of appropriate clinics/appointment types |  | Including Branch surgery locations
| 30 | Is the user able to book an appointment? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 31 | Is the user able to book an appointment at a branch/different location? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 32 | Is the user able to change/re-book the appointment whilst in the same consultation? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 33 | Is a SMS sent to the patient (if configured)? | The patient receives a SMS and it contains the correct appointment and location details
| 34 | Is the user able to change/re-book the appointment after the consultation is complete (the patient calls back in 2 hours)? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 35 | Is the user able to cancel the appointment after the consultation is complete (the patient calls back in 2 hours)? | The user is presented with a confirmation that the booking has been succesful The appointment at the surgery is cancelled within their IT system
| 36 | Is a referral message sent successfully? | The 111 provider gets confirmation tat the referral was sent
| 37 | Is a referral message received successfully? | The surgery will be able to view the referral information in their surgery system
| 38 | Is the user presented with no appointments when no appointments are available? | The user should see no appointments are being displayed and appropriate message is displayed
| 39 | Is the user able to run the standard GP Connect reports? | User can locate the reports and successfully run them
Dx08 | 40 | Is the user able to select the appointment botton for this DX code? | The user can select the button and no errors are presented
| 41 | Is the user presented with a list of appointment slots to book into when pressing the appointment button? | The user should see all the appointments available above (apart from those already booked or taken)
| 42 | Is the user presented with all clinics that have been made available to the 111 service? | The user should be presented with a list of appropriate clinics/appointment types |  | Including Branch surgery locations
| 43 | Is the user able to book an appointment? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 44 | Is the user able to book an appointment at a branch/different location? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 45 | Is the user able to change/re-book the appointment whilst in the same consultation? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 46 | Is a SMS sent to the patient (if configured)? | The patient receives a SMS and it contains the correct appointment and location details
| 47 | Is the user able to change/re-book the appointment after the consultation is complete (the patient calls back in 2 hours)? | The user is presented with a confirmation that the booking has been succesful The surgery can view the appoinment within their IT system
| 48 | Is the user able to cancel the appointment after the consultation is complete (the patient calls back in 2 hours)? | The user is presented with a confirmation that the booking has been succesful The appointment at the surgery is cancelled within their IT system
| 49 | Is a referral message sent successfully? | The 111 provider gets confirmation tat the referral was sent
| 50 | Is a referral message received successfully? | The surgery will be able to view the referral information in their surgery system
| 51 | Is the user presented with no appointments when no appointments are available? | The user should see no appointments are being displayed and appropriate message is displayed
| 52 | Is the user able to run the standard GP Connect reports? | User can locate the reports and successfully run them
These details will need to be updated after speaking to the GP Connect Team
These details will need to be updated to include the relevent stakeholders. Some of the stakeholders will need to part of the core test team
Details of the Surgery will need to be collected
Record the GP IT System that will need to be tested and dates for testing
This is a test patient that should be used. The patient has a home address of the surgery to ensure we can find the relevent service on the DOS
This test plan convers the main operational tests for a consumer for the DX codes that support appointment booking. They also include some negative tests
Details of the Surgery will need to be collected